A yearlong PD series for schools attempting to amplify PBLs from projects and activities into Gold Standard PBLs and, eventually, cross-curricular PBLs: Highlighted Items appear in the Appendix

| Session | Focus | Primary Goal | Main Teacher Artifact | Needed for Session |
| --- | --- | --- | --- | --- |
| Fall Day 1 Aug 21 | PBL at IA | What is a Gold Standard PBL? Identify one project to build or revise into Gold Standard. | - PBL One-Page Planner | - PBL One-Page Planner - Gold Standard Review Checklist - Student Workload & Project Calendar |
| Fall Day 2 Oct 30 | Authenticity by Design | Strengthen the public product, audience, real-world relevance of a PBL. ID roles that business partners/community can play in PBL | - Authenticity and Public Product Planner - Business Partner Request Form | - Authenticity and Public Product Planner - Business/Community Partner Request Form |
| Fall Day 3 Dec 11 | Assessments, Checkpoints, and Pacing | Map your checkpoints, gradebook alignment, and manageable pacing for students | - Checkpoint and Assessment Planner - Draft Full PBL Unit | - Checkpoint and Assessment Planner - Full Gold Standard PBL Unit Planner |
| Spring Day 4 Jan 15 | PBL Implementation Review and Reflection | Reflect on pilot PBL/implementation data and use to inform Spring semester PBL | - Post Project Teacher Reflection - PBL One-Page Planner | - Post-PBL Teacher Reflection survey - Student feedback results - Gold Standard Review Checklist - PBL One-Page Planner |
| Spring Day 5 April 2 | Assessment, Checkpoint, Pacing and Authenticity for Spring PBL | Strengthen the public product, audience, real-world relevance of a PBL. ID roles that business partners/community can play in PBL Map your checkpoints, gradebook alignment, and manageable pacing for students | - Authenticity and Public Product Planner - Business Partner Request Form - Checkpoint and Assessment Planner - Draft Full PBL Unit | - Authenticity and Public Product Planner - Business/Community Partner Request Form - Checkpoint and Assessment Planner - Full Gold Standard PBL Unit Planner |
| Spring Day 6 May 14 | Finalize, Map Next Year | Finalize Fall PBL Unit Plan for ’27 – ‘28 Map project timeline for ’27 – ‘28 Develop accountability cycle | - Full PBL Unit - Annual Project Map for school (all teachers, shared document) | - Full Gold Standard PBL Unit Planner - Annual Project Map/Calendar - Gold Standard Review Checklist |

PD Day 1: Re-set the Bar: What Gold Standard PBL Looks like at [School Name]

Purpose: To establish a shared understanding of the difference between project-like activities and true Gold Standard PBL unit.

Desired Outcomes for the day:

- Identify a project you have used that you would like to revise as a Gold Standard PBL

- Complete a PBL One-Page Concept Planner

- Analyze current project alignment with Gold Standard expectations

Agenda 2 Hours Morning, 2 Hours Afternoon

| Time | Segment | Focus and Action |
| --- | --- | --- |
| 20 min | Welcome and framing of work | Name the current reality: teachers know PBL language, but projects lack some qualities of Gold Standard & students feel overloaded by too many simultaneous projects. |
| 30 min | Calibration protocols: Sort your Projects | Teachers use the Gold Standard Review Checklist to determine whether a past PBL was more of a culminating activity, a PBL-lite, or a Gold Standard PBL |
| 10 min | Day 1 Track + Transition | Teachers/PLCs sorted into tracks: Build/Convert – want to refresh totally or have no PBL Refine/Amplify – want to modify existing project into Gold Standard |
| 60 min | Track-based work time | Teachers complete either PBL One-Page Planner (Build/Convert) or work on Full PBL Unit Planner (Refine/Amplify) |
| Lunch | Lunch | Lunch |
| 10 min | Framing of work for afternoon | Students feel overburdened by PBLs all happening around the same time of year |
| 10 min | Whole school PBL calendar | Teachers/PLCs update their initial implementation timeline to a shared calendar + review Fall PBL timeline for noticeably large burdens on students |
| 20 min | Implementation Refresh + Transition | Teachers/PLCs determine if they can move units to lighten the student burden for the Fall semester |
| 40 min | Critique and Feedback Session | Critique and Feedback: Teachers/PLCs get eyes on their current PBL-One Page Planner OR Full PBL Unit Planner Must have on planner: Title, Driving Question/Challenge, Audience, Priority Standards, and at least one area that needs suggestions or improvement Feedback Gallery Walks with Sticky Notes Color coordinated for I like I wish I wonder or another method of feedback |
| 40 min | Revise and Finalize Work Time | Teachers take feedback and finalize their One-Page Planner or continue draft of Full PBL Unit Planner |

Deliverables:

- Completed PBL One-Page Planner OR in-progress Full PBL Unit Planner

- Initial Gold Standard Review Checklist

- Project implementation timeline

Next PD Day Focus:

Authenticity by Design: Creating PBLs with real-world clients/users, authentic products, and involving business partners and/or community in the PBL process.

PD Day 2: Authenticity by Design: Focus on Public Product, Real Audience, and Business Partner/Community Opportunities

Purpose: Strengthen the authenticity of PBLs by helping teachers design meaningful public products, identify real audiences or clients/users for final products, and plan for business partner/community involvement.

Desired outcomes for the day:

- Strengthen the real-world relevance of a project

- Define a meaningful audience or client or user for final products

- Clarify where in your PBL that business partner or community involvement adds value

- Draft a business partner or community involvement request

| Time | Segment | Focus and Action |
| --- | --- | --- |
| 20 min | Welcome and framing of work | What is authenticity? What levels of authenticity are we incorporating? Teachers examine their PBLs and identify whether products are for the teacher and gradebook or for an authentic user |
| 30 min | Mini lesson: The Authenticity Ladder | Introduce levels of authenticity and the roles that partners can play in a PBL: at launch, fieldwork opportunities, critiques, audience or client/user, mentoring. |
| 30 min | Teacher/PLC Protocol: Strengthen the Public Product | Teachers/PLCs use the Authenticity & Public Product Planner to clarify what students will create, who will care, and why it matters beyond a grade. |
| 10 min | Break + Transition | Short transition |
| 30 min | Interdisciplinary Work Time and Reviews | Teachers work in interdisciplinary groups to revise project ideas using the authenticity ladder, identify real constraints and barriers to authenticity, and refine public products. |
| Lunch | Lunch | Lunch |
| 30 min | Teacher/PLC Protocol: Strengthen Authenticity and Public Product | Teachers/PLCs come back together to refine the authenticity and public product based upon the interdisciplinary work session. |
| 50 min | Business Partner and Community Planning | Teachers have time to explore business partner list Teachers complete the Business Partner/Community Request form with specifics about the role the partner will take in the PBL: supporting launch, offering fieldwork, providing critique and feedback during prototyping phases, being a real-world client for the final product, providing mentorship and guidance during ideation…etc. |
| 10 min | Break | Break |
| 30 min | Full PBL Unit Planner | Move from PBL One-Page Planner to Full PBL Unit Planner; continue revisions of Full PBL Unit Planner from Day 1 |

Deliverables:

- Completed Authenticity and Public Product Planner

- Defined audience and public product

- Partner Request Form submitted

- Revisions to PBL Planners

- Nearly completed Full PBL Unit Planner (assessments and checkpoints not fully developed)

Next PD Day Focus:

Assessments, checkpoints, and grading full PBL units.

PD Day 3: Assessments, Checkpoints, Grading, & Pacing + Student Workload

Purpose: Make PBLs manageable by aligning them to select standards, having checkpoints, pacing, all while meeting district grading requirements 2, 3, 3.

Desired Outcomes for the day:

- Build checkpoints and feedback points into PBL

- Align checkpoints and assessment tools to standards and products

- Map your project assessments to majors, minors, and practice grades

- Check pacing to fit current classroom pacing/constraints on curriculum needs

| Time | Segment | Focus and Action |
| --- | --- | --- |
| 10 min | Welcome and framing of work | Address the district requirements for grading windows: 2 majors, 3 minors, 3 practice and constraints upon PBLs |
| 10 min | Mini lesson: How do I grade this? | Formative vs summative assessment strategies, embedding critique and revision into grading, rubrics for behavior-based student commitments and how these can be used for classroom management and project management (collaboration, communication, etc.) |
| 40 min | Gradebook Mapping Activity + Transition | Teachers/PLC identify or create multiple checkpoints for learning within the PBL unit. Teachers/PLC map project checkpoints into practice, minor, or major grades. |
| 20 min | Protocol: Checkpoint Review | Interdisciplinary groups review one another’s draft checkpoints for pacing, critique and revision timing, clarity, and connection to standards. |
| 10 min | Break | Break |
| 30 min | Work time by track Build/Convert Refine/Amplify | Teachers complete the Checkpoint and Assessment Planner and pacing checks |
| Lunch | Lunch | Lunch |
| 10 min | Framing of Work | Cross-curricular PBLs: when, how, and why |
| 20 min | Teachers/PLCs Work Time | Teachers/PLCs update Spring PBL timeline and implementation |
| 10 min | Identify Cross-Curricular Opportunities | Teachers/PLCs review shared Spring PBL timeline calendar to ID possible cross-curricular opportunities |
| 60 min | Cross-curricular planning | Teachers/PLCs begin the process of planning potential cross-curricular PBLs for the Spring semester Option 1: Continuation of PBL from another course/class, refining of public product to incorporate standards and student learning experiences Option 2: PBLs happening at the same time because of overlapping standards and student learning experiences |

Deliverables:

- Completed Checkpoint and Assessment Planner

- Gradebook alignment

- Partial draft of cross-curricular PBL for Spring

- Completed Full Gold Standard PBL Planner

Next FULL PD Day Focus:

Spring PD Day 1: Student final products, teacher notes on pacing/planning of implemented PBL, student experience data.

Next .5 PD Day Focus:

Flex Friday Sessions for the Spring semester.

PD Day 4: Learn from Implementation: Reflection, Student Experiences, and Project Revision

Purpose: Use real classroom evidence to identify areas of weakness or gaps in PBL and revise for future stronger implementation.

Desired outcomes for the day:

- Share student work samples with peers

- Analyze student feedback for weaknesses or gaps in the PBL

- Revise scaffolding, pacing, and project structure

| Time | Segment | Focus and Action |
| --- | --- | --- |
| 20 min | Welcome and framing of work | Why reflection on practice in the classroom matters. Teachers do a quick write on successes, challenges, surprises, and student stress points. |
| 20 min | Mini review with peers | Identify where common issues may fall within your own PBL: weak audience/inauthentic audience for public product, unclear product expectations or end users, rushed critique and revision protocols, student overload, pacing, minimal assessment checkpoints, etc. |
| 40 min | Artifact Review Protocol + Transition | Teachers/PLCs analyze student products, checkpoint results, survey data, and implementation notes from Fall PBL. Teachers complete the Post Project Teacher Reflection. |
| 40 min | Artifact Review Protocols Interdisciplinary team | Interdisciplinary teams provide similar reviews of results, data, notes, and products and provide feedback to one another about improving overall PBL. |
| Lunch | Lunch | Lunch |
| 75 min | Revision Work Time | Teachers/PLCs work to refine launch events, scaffolds, audience involvement, assessment plans, final product expectations, real user information, workload expectations, and finalize the Full PBL Unit Plan for next implementation. |
| 25 min | Revision Work Time | Teachers/PLCs use the Gold Standard Review Checklist to assess whether the revised PBL is stronger. |
| 10 min | Exit Commitments | Each teacher or PLC identifies one revision, one simplification, and one area where more support is still needed for the next implementation. |

Deliverables:

- Completed Post Project Teacher Reflection

- Revised Full Unit PBL Planner

Next Full PD Day Focus:

Spring PBL revisions and intentional cross-curricular planning time for PBLs

PD Day 5: Designing Powerful Cross-Curricular PBLs

Purpose: Transform siloed PBLs into meaningful cross-curricular activities that either run concurrently with multiple teachers or are continued from one subject/class to another.

Desired outcomes for the day:

- Align teachers around a shared purpose

- Identify where cross-curricular overlap occurs in the year/semester

- Clarify products and prototypes, along with evidence students will produce during their PBL

- Design at least one potential cross-curricular PBL with another teacher from a different core content area or pathway

| Time | Segment | Focus and Action |
| --- | --- | --- |
| 20 min | What makes cross-curricular learning worthwhile? | Discuss shared PBL calendar and implementation overlaps – students feel overburdened Cross-curriculars reduce the burden on students by reducing the number of concurrent PBLs in the building Cross-curriculars allow students to see overlapping curriculum through discipline specific lenses |
| 30 min | Analyze the existing barriers and propose solutions | Teachers discuss the current barriers to planning and implementing a cross-curricular PBL Teachers design solutions to these barriers |
| 10 min | Break | Break |
| 60 min | Cross-curricular planning time | Making use of potential curricular overlaps from the shared calendar website, teachers identify colleagues to work with and begin the process of planning based on logistics, final products, etc. |
| Lunch | Lunch | Lunch |
| 60 min | Cross-curricular planning time | Teachers continue cross-curricular planning time and begin to combine PBL Unit Plans/One-pagers into a cohesive working plan |
| 25 min | Gallery Walk/Critical Feedback | Teams review one another’s current plan for feasibility, coherence, to generate ideas about final product, to check for authenticity levels, etc. |
| 35 min | Cross-curricular planning time | Final check-in with new PBL colleague groups to update business/community partner involvement, authenticity of products and audience, assessments and grading norms, etc. |
| 10 min | Exit commitments | PBL colleague groups create a timeline for collaboration to continue finalizing cross-curricular PBL |

Deliverables:

- Planning calendar with dates and times of next “PLC”

- Partnership and resource needs identified and submitted to business/community liaison

- In Progress Full PBL Unit Planner

Next Full PD Day Focus:

Full PBL Unit Planners, Cross-curricular progress, Schoolwide mapping of PBLs, Spring PBL Reflections

PD Day 6: Finalize, Map, Reflect, Celebrate

Purpose: Finalize cross-curricular PBL plans, map schoolwide PBL implementation for Fall semester and ID potential cross-curricular opportunities, establish an accountability system, reflect on Spring PBL implementation, celebrate progress.

Desired outcomes for the day:

- Finalize cross-curricular PBL unit

- Complete Fall semester PBL map for school

- ID schoolwide workload pressure points for Fall

- ID potential Fall cross-curricular opportunities

- Establish accountability cycle for future PBL implementations

- Reflect on Spring PBL implementation

- CELEBRATE HOW FAR WE’VE COME

| Time | Segment | Focus and Action |
| --- | --- | --- |
| 15 min | Celebration of progress | Large shift in PBLs toward stronger authenticity, cross-curricular reality, fewer silos and isolated projects, and a better student experience |
| 40 min | Artifact Review Protocol + Transition | Teachers/PLCs analyze student products, checkpoint results, survey data, and implementation notes from Spring PBL. Teachers complete the Post Project Teacher Reflection |
| 65 min | Finalize cross-curricular PBL | PBL colleague groups work to finalize their Full PBL Unit Planner for implementation in the Fall semester |
| Lunch | Lunch | Lunch |
| 30 min | Update schoolwide PBL map for Fall | PBL colleague groups upload data to schoolwide PBL map for the entire following school year to identify months where student workload burdens may be too severe and discuss if logistics can change, also ID pressure points for Spring re: testing season |
| 50 min | Teachers develop accountability cycles for next school year | Teachers/PLCs/PBL colleague groups work to develop non-negotiables for accountability cycles for upcoming school year (large post-it note) Gallery Walk and review/revision of non-negotiables – teachers review all suggestions, adding stars to common expectations, question marks for clarification, and x’s for disagreement Whole group share-out: Whole group discusses the results and finalizes the accountability expectations for future PBL implementations |
| 40 min | Celebration Showcase | Teachers showcase student final products and favorite lessons from the school year |

Deliverables:

- Completed cross-curricular Gold Standard PBL Unit Planner

- Completed annual project mapping

- Clear accountability cycles for future implementations

Appendix A: Gold Standard Review Checklist

Use this checklist to determine whether a project is ready to launch as Gold Standard PBL or to reflect upon the implementation of a PBL from prior years. Rate each area, note evidence, and identify revisions needed before the first/next implementation.

1 = Not Yet    2 = Developing    3 = Strong    4 = Ready to Launch

| Project Title: ____________________________ | Teacher(s): ____________________________ |
| --- | --- |
| Course(s): ____________________________ | Reviewer: ____________________________ |
| Date: ____________________________ | Status: ____________________________ |

| Category | Descriptor | Rating | Evidence / Notes |
| --- | --- | --- | --- |
| Driving Question / Challenge | The project is anchored by a meaningful question, problem, or challenge. |  |  |
| Standards Alignment | Priority standards, learning targets, and durable skills are clearly articulated. |  |  |
| Authenticity | The project reflects a meaningful real-world context and application. |  |  |
| Public Product | Students create something for an audience beyond the teacher and gradebook. |  |  |
| Audience | The audience is specific, appropriate, meaningful, and extends to a real-world user. |  |  |
| Critique and Revision | There is at least one planned cycle of critique and revision. |  |  |
| Student Voice and Choice | Students have meaningful opportunities to make decisions about product, research, or topics. |  |  |
| Assessment | Rubrics, checkpoints, and grading plans are clearly outlined and articulated. |  |  |
| Manageability | The project is realistic in workload, pacing, and logistics. |  |  |
| Business Partner Integration (if applicable) | Business partner involvement is purposeful and clearly defined. |  |  |
| Reflection | There are opportunities for students to reflect upon their process throughout the project. |  |  |

| Overall Strengths 1. ________________________________ 2. ________________________________ 3. ________________________________ | Priority Revisions Before Re-Launch 1. ________________________________ 2. ________________________________ 3. ________________________________ |
| --- | --- |

Appendix B: Authenticity and Public Product Planner

Project Title: 							Teacher(s):

Course/PLC: 							Department:

- Real-world connection:

What real-world issues, challenges, questions, or industry/community relevance exists in this project?

Why/How does this matter beyond the school?

Who deals with this type of issue in the real world?

- Authenticity Self-Check

Rate each area from 1(Not Yet) to 4(Strong)

| This project is grounded in a meaningful, real-world issue, question, challenge, or has industry/community relevance. | Rating: | Evidence: |
| --- | --- | --- |
| Students are producing work for someone beyond the teacher/gradebook. |  |  |
| Students receive feedback from authentic or intended audience/user and/or industry export. |  |  |
| This work reflects real roles, constraints, or standards. |  |  |
| The final product could contribute to the world in some way through informing, supporting, and solving real-world problems. |  |  |
| The final product was developed to be used by a real-world client. |  |  |

- Public Product Design

What did students create?

Who saw the final product?

What did the audience do with the final product? (Check all that apply)

☐	Give feedback

☐	Ask questions

☐	Use the product

☐	Judge proposals

☐	Select ideas

☐	Request revisions

☐	Other: Click or tap here to enter text.

Where and how was the product made public? (Check all that apply)

☐ Panel presentation

☐ Exhibition

☐ Digital publication

☐ Pitch sessions

☐ Community event

☐ Website

☐ Other: Click or tap here to enter text.

- Audience ladder: Check the highest level that currently applies to your PBL:

☐ Teacher only

☐ Other students/classes

☐ School staff/internal audience

☐ Families/school community

☐ Business or community audience

☐ Real client/ end user/ decision-maker

What would move the product one level higher and allow for a real client/end user?

- Strengthen Authenticity

☐ Which of the following could be added to the project?

☐ Local problem or community need

☐ Stakeholder interviews

☐ Real data collection

☐ Business partner/industry level critique of prototype

☐ Product with real use by a client

☐ Public sharing beyond school

☐ Fieldwork / site visits

- Final Revisions Before Re-Launch

List three changes that will make the project more authentic.

Appendix C: Checkpoint and Assessment Planner

Use this to make projects manageable, build in feedback opportunities, and align projects to district grading expectations.

Teachers(s):

Course(s):

Project Title:

Implementation Dates:

- Final product

What is the final product?

How will the final product be delivered? (Presentation, panel, defense, etc.)

Final audience/user:

- Project Checkpoints

Checkpoint 1:

Due Date/ Sequence:

What students submit or show:

Teacher feedback type:

Grade type (practice, minor, major):

Checkpoint 2:

Due Date / Sequence:

What students submit or show:

Teacher feedback type:

Grade type (practice, minor, major):

Checkpoint 3:

Due Date / Sequence:

What students submit or show:

Teacher feedback type:

Grade type (practice, minor, major):

Checkpoint 4:

Due Date / Sequence:

What students submit or show:

Teacher feedback type:

Grade type (practice, minor, major):

Checkpoint 5:

Due Date / Sequence:

What students submit or show:

Teacher feedback type:

Grade type (practice, minor, major):

- Assessment types

Formative assessments:

Peer feedback opportunities:

Self-assessment and reflection opportunities:

Summative assessments:

- Gradebook Crosswalk

Practice Grades:

Minor Grades:

Major Grades:

- Individual Accountability:

If students work in teams, how will individual learning be assessed?

- Revision expectations:

At which checkpoint(s) will students revise?

Which evidence of revision is required?

- Pacing Check

What direct instruction or mini lessons must be embedded during the project?

- Risk Points

Where might students get stuck?

What supports/scaffolding will help them move forward?

- Final Check for assessment alignment……

☐  Checkpoints build towards the final product

☐  Feedback happens before the final submission

☐  Students have enough time to revise

☐  Students have opportunities to reflect on process during the duration of the project

☐  The grading plan is clear for students

☐  The pacing is realistic

Appendix D: Post Project Teacher Reflection

Use this tool to capture what worked, with did not, and what needs to improve.

Teacher(s):

Course(s):

Project Title:

Implementation Dates:

- Briefly describe how the project unfolded

- What worked well? (considerations: student engagement, rigor, authenticity, checkpoints, product quality, audience responses, etc.)

- What did not work as well? (considerations: pacing, grading expectations, group work issues, product quality, workload, timing, etc.)

- Gold-Standard Self Assessment – Rate each 1 to 4

Driving Question/Challenge:

Authenticity:

Public Product/Audience:

Student voice and choice:

Critique and revision:

Reflection:

Assessment alignment:

Project alignment with learning standards:

- Student experience

How did students respond to the project? Were responses consistent throughout or different during different phases like the launch, a specific checkpoint, etc.

What evidence supports this?

- Workload Check

Did the project feel manageable for students?

Why or why not?

- Revision for next time

What should be revised before this project is taught again?

- Partner /Audience Reflection

If applicable, how effective was partner or audience involvement?

Appendix E: One Page PBL Planner

Purpose: Use this to have a one-page reference when moving an activity towards a PBL

Teacher(s):

Courses(s):

Department:

Grade level(s):

Semester/Quarter:

Project Implementation Window:

Project Title:

Driving Question/Problem/Challenge: What meaningful question, challenge, or problem will anchor this project?

Priority Standards and Learning Objectives: What are the most important standards, learning objectives, essential knowledge, and skills/competencies that students will learn and apply?

Authenticity: How does this PBL reflect authentic, real-world contexts, constraints, products?

Public Product/Audience: How does this PBL allow students to produce a product for a real-world client, real-world use, and extend the lessons beyond the teacher, gradebook, and school?

Critique and Revision: Where in the PBL will students have opportunities to receive feedback in a structured activity and to revise based upon the feedback?

Student voice and choice: Do students have meaningful opportunities to make decisions about final product, research paths, topics, etc.?

Reflection: Where in the PBL do students have the opportunity to reflect upon their learning process, skill development, etc.?

Assessments: Rubric, checkpoints, and grading plans are clearly outlines and articulated.

| Overall strengths | Priority Revisions Before First/Re-deployment |
| --- | --- |

Appendix F: Full PBL Unit Planner

Purpose: To design a full PBL Unit with all components of Gold Standard PBLs and space for daily pacing calendars. Personally love the PBL Works Planner and would highly recommend adopting their framework.

PBL Works Unit Planner

Appendix G: Business/Community Partner Request Form

Purpose: Use this form to help school liaison to connect community with teachers to fit needs within the PBL.

Teacher(s):

Email:

Course:

Department:

Project Title:

Grade level(s):

PBL Implementation Window:

Project Summary:  In 3-5 sentences, describe the project and what students will be doing/producing.

Driving Question/Challenge/Problem: What anchors the project?

Purpose of partner involvement: Why is a partner needed? What will a partner add to the project?

Type of support requested/role of partner in PBL: Check all that apply:

☐Help define a real-world challenge

☐Launch event/speaker/kickoff

☐Expert interview

☐Midpoint critique or draft feedback

☐Final audience/panel

☐Fieldwork/site visit host

☐Mentorship

☐Real product client

☐Product usefulness feedback

☐Other  Click or tap here to enter text.

Partner Role: Provide a short description of the specifics of the role you ID’ed above. What will your partner be doing?

Preferred Partner Type: examples: health professionals, engineers, IT professionals, non-profit representative, university faculty, entrepreneur, district staff, government agency, etc.

Student Product: What will students produce? What is its real-world use?

Timeline and format:

Dates or windows needed:

Length of engagement/number of engagements:

Preferred format: ☐   In-person; ☐   Virtual; ☐    Either

Preparation needed: What materials, background information, student work should the partner receive in advance to help them better understand the PBL and their role?

Logistics:

Technology needs:

Transportation needs:

Number of students involved:

Additional notes: Anything else liaison should know?

Follow-up plan:

How will students or the teacher thank the partner and share the outcomes?